## 01_README
Item | Value / Instruction
Workbook purpose | Founder-facing release review master for StayOS: web acceptance, decision collection, differentiation capture, and release readiness — before mobile implementation.
Prepared | 2026-09-20 · branch product-completion-review @ 2f602b0
SECURITY RULE | Do NOT store production passwords, API keys, AWS secrets, DB credentials, OTP secrets, private tokens, signing keys or recovery codes in this workbook. Names/status only.
Benchmark status | CLOSED — 204 requirements, 0 unresolved implementable gaps. See docs/benchmark/FINAL_AIRBNB_BENCHMARK_CLOSURE.md. Do not reopen.
Order of work | 1) 05_WEB_ACCEPTANCE review on the Vercel preview → 2) record findings in 06_FOUNDER_OBSERVATIONS → 3) answer 04_FOUNDER_DECISIONS → 4) enter ideas in 07_DIFFERENTIATION_IDEAS → 5) review 08_RELEASE_BLOCKERS + 17_MANUAL_ACTIONS → 6) only then mobile (15_MOBILE_READINESS).
How to fill | Dropdowns provided where useful. Founder Choice stays blank until selected. Options come from repository evidence only; engineering does not pick.
Web preview | https://stayos-814l6q390-islam-elbaz-s-projects.vercel.app (302 → /en; /ar for Arabic)
API | https://stayos-demo-production.up.railway.app (/docs Swagger)
Login | Dev Login on /en/auth/login — Guest seed-accept-gues-0000-000000000001 · Host seed-host-0000-0000-000000000002 · Admin seed-admin-0000-0000-000000000001
Known limitation | Uploads (photos, payment proof, KYC docs) return controlled 503 until AWS storage vars are set — release blocker, not a defect.
Source registers | docs/release/FOUNDER_DECISION_REGISTER.md · docs/release/FOUNDER_WEB_ACCEPTANCE_REGISTER.md · docs/benchmark/* · docs/RELEASE_TECHNICAL_HANDOFF.md

## 02_PROJECT_STATE
Item | Value | Evidence / Source
Repository | github.com/islamelbaz2010/StayOS | git remote
Branch | product-completion-review (109 commits ahead of main; main untouched) | git
HEAD | 2f602b0 docs(benchmark) on top of 0d2b14e feat(benchmark) | git log
Phase | Phase 0 active (commercial validation); Phase 1 engineering authorized per DEC-011; public launch deferred until closed alpha (DEC-017) | .ai/CURRENT/DECISION_LOG.md
Benchmark | CLOSED — PASS with founder decisions | docs/benchmark/FINAL_AIRBNB_BENCHMARK_CLOSURE.md
API paths | 156 | apps/web/lib/openapi.json (regenerated 2026-09-20)
Migrations | 41 versions · head 040_candidate_governorate | alembic heads
Backend tests | 1160 passed · 80.60% coverage | pytest this pass
Auth/security tests | 89 passed | pytest test_auth* test_security
Frontend | typecheck ✓ · lint ✓ · Vitest 12/12 · production build ✓ | npm run type-check/lint/test/build
Mobile | Expo/RN tsc --noEmit ✓ · preview APK only | apps/mobile
API deploy | Railway stayos-demo · ae8267c4 · SUCCESS on 2f602b0 | Railway list-deployments
Worker deploy | Railway · b5c774f4 · SUCCESS on 2f602b0 | Railway
Beat deploy | Railway · 55b95446 · SUCCESS on 2f602b0 | Railway
Postgres/Redis | Railway-managed, healthy (/health db+redis ok) | live check earlier
Web deploy | Vercel preview live; no production domain | Vercel/CORS evidence
Storage | AWS vars defined but EMPTY on Railway → presign endpoints return controlled 503 | earlier live verification
Payment | Manual collection; placeholder account values; processor undecided (FD-01) | config.py
OTP | Akedly integrated; live SMS delivery unverified | test_auth_otp_akedly.py
Google Maps | Malformed var name on worker/beat; rotation unconfirmed | handoff §12
Sentry | Code present; DSN not set | handoff
Backups | Not verified/configured — manual action | handoff
Domain/CORS | Project-scoped CORS regex set; prod domain TBD | 418dca8
ENVIRONMENT | dev/staging implied (dev-token reachable); must be production at launch | handoff

## 03_BENCHMARK_CLOSURE
Metric | Count / Value | Notes
Total requirements | 204 | 14 domains
A — IMPLEMENTED — BENCHMARK-SUPPORTED | 187
B — PARTIALLY IMPLEMENTED | 1 | PAY-02 payment instructions (placeholder accounts — release blocker, not benchmark gap)
C — NOT IMPLEMENTED | 0
D — IMPLEMENTED BUT BENCHMARK-AMBIGUOUS | 0
E — IMPLEMENTED BUT NON-BENCHMARK | 2 | listing importer; discovery moderation
F — TECHNICAL-ONLY | 2 | operations metrics; auditability
G — CONFLICTING | 0
H — FOUNDER DECISION | 12 | see 04_FOUNDER_DECISIONS
Implementable gaps found | 2 | availability calendar; review keyword search
Implementable gaps remaining | 0 | both implemented in closure pass (0d2b14e)
Gate result | PASSED — subject to founder decisions | register §5
Register | docs/benchmark/FINAL_AIRBNB_BENCHMARK_CLOSURE.md | authoritative
Differentiation gate | docs/benchmark/STAYOS_DIFFERENTIATION_GATE.md | unlocked for code; ideas gated on founder entry

## 04_FOUNDER_DECISIONS
ID | Decision | Current implementation | Why a decision is required | Options (from repo evidence) | Dependencies | Impact if deferred | Founder Choice | Status | Notes
FD-01 | Payment processor | Manual collection; Paymob+Stripe code dormant; DEC-015 scopes Stripe to international cards | DEC-004/MASTER_CONTEXT=Paymob vs FLOWS/BACKLOG=Stripe — unresolved documented conflict | Manual only (alpha) ¦ Paymob+Stripe split ¦ Stripe only | Legal entity; CBE PSP analysis; FD-12 account | Manual flow works; online checkout blocked |  | OPEN
FD-02 | KYC automated-verification architecture | Textract/Rekognition coded; unavailable in me-central-1; manual admin review proven | Providers absent in chosen region; manual viable at alpha volume | Manual only (alpha) ¦ ML in other AWS region ¦ Alternative provider | AWS region decision; PDPL review | KYC works manually |  | OPEN
FD-03 | Guest-type occupancy semantics | Booking splits adults/children/infants; search single guests count; max_guests on total | Whether infants/children count toward capacity is a business rule | Infants don't count ¦ All types count ¦ Host-configurable | Listing max_guests; DIS-06 | Search stays single-count |  | OPEN
FD-04 | Review report + moderation policy | Simultaneous publication; no report/moderation workflow | Report reasons, removal criteria, appeals are policy | No moderation (alpha) ¦ Report→admin queue ¦ Automated screening | Admin tooling; legal | Reviews unmoderated |  | OPEN
FD-05 | Booking alterations | Cancel+rebook only | Alterations need repricing + host-approval rules | Cancel+rebook only ¦ Host-approved alteration | Refund+calendar engines | Guests must rebook |  | OPEN
FD-06 | Host pre-approval | Not implemented | Commits host before formal request | Skip ¦ Pre-approval token | Messaging+booking | Normal request flow works |  | OPEN
FD-07 | Special offers | Not implemented | Custom pricing rules cannot be invented | Skip ¦ Host custom quote on thread | Pricing engine | Standard pricing only |  | OPEN
FD-08 | Length-of-stay discounts | No weekly/monthly discount field | Pricing policy | None (alpha) ¦ Host-set weekly/monthly % | Pricing+quote | No LoS discounts |  | OPEN
FD-09 | Smart/dynamic pricing | Not implemented; DEC-018 postpones until 1,000+ listings/50K txns | Strategy + data dependency | Keep DEC-018 deferral ¦ Rule-based earlier | Transaction data | No pricing assistance |  | OPEN
FD-10 | Multi-currency display | EGP-only | Single-market launch decision | EGP only (alpha) ¦ Multi-currency display | FD-01 | EGP only |  | OPEN
FD-11 | Mobile framework | Expo/RN preview; DEC-014 gates on 'ADR-016' — NUMBER COLLISION: ADR-016 already used by ePOS governance ADR; DEC-018 postpones native until 100+ bookings | Framework commitment needed before mobile work | Keep Expo/RN ¦ Native rewrite ¦ PWA for alpha | New ADR number; OPPO P0 fixes | Mobile stays preview APK |  | OPEN
FD-12 | Real collection account | Placeholder bank/Vodafone values in config | Guests see placeholder payment data | Founder-provided account details | Legal entity (account name) | Checkout unsafe for real money |  | OPEN
FD-13 | Legal entity + marketplace characterization | No entity data; dossier lists required inputs | Gates CBE analysis, tax, contracts | Founder/counsel: legal form, CR, tax card, HQ, activity | Counsel engagement | All regulated blockers open |  | OPEN
FD-14 | Analytics provider | DEC-013 deferred to Sprint 1 | Funnel observability | Keep deferral ¦ Pick provider now | — | No product analytics |  | OPEN
FD-15 | OTP provider | Akedly integrated; live delivery unverified | SMS must deliver for real users | Akedly ¦ Alternative (Twilio vars exist) | Provider credits/config | Dev-login only for acceptance |  | OPEN
FD-16 | ENVIRONMENT=production cutover | Dev-token reachable (dev/staging implied) | Dev Login must not reach public users | Flip at launch ¦ Keep dev for acceptance now | Production domain | Correct for current phase |  | OPEN

## 05_WEB_ACCEPTANCE
ID | Surface | Route | Current behavior (verified) | Benchmark status | Class | Founder Verdict | Notes
WEB-CON-01 | Landing | /en | CategoryChips, PopularDestinations, TrustSignals, RecentlyViewed | Compliant | A
WEB-CON-02 | Search results | /en/search | URL-driven filters, list/map, bounds, sort, all-in total on date-filtered cards | Compliant | A
WEB-CON-03 | Filters | /en/search | Full filter set; guest-type split pending FD-03 | Compliant/Decision | A/D
WEB-CON-04 | Map | /en/search | Bounds-driven results | Compliant | A
WEB-CON-05 | Listing cards | /en/search | Nightly + all-in total w/ dates | Compliant | A
WEB-CON-06 | Listing detail | /en/listings/{id} | Gallery, fees, NEW availability calendar, reviews w/ NEW keyword search, host card, map, share, favorite, contact, similar | Compliant | A
WEB-CON-07 | Booking panel | listing detail | Calendar select, guest split, quote, KYC gate, instant-book badge | Compliant | A
WEB-CON-08 | Request-to-book | listing detail | 24h host expiry, accept→pay→confirmed | Compliant | A
WEB-CON-09 | Instant Book | instant-book listing | Auto-accept→pay | Compliant | A
WEB-CON-10 | Checkout/payment | /en/checkout/{bookingId} | Manual instructions PLACEHOLDER accounts, proof upload 503 until AWS, 24h deadline | Compliant; RB-01/RB-02 | C
WEB-CON-11 | Trips | /en/bookings | States+filters, cancel preview, review eligibility, check-in gating | Compliant | A
WEB-CON-12 | Cancellation | trip detail | Tiered refund preview→status | Compliant | A
WEB-CON-13 | Messaging | /en/messages | Inquiry/reservation/support threads, unread, notify | Compliant | A
WEB-CON-14 | Notifications | in-app | Outbox-driven + deep links | Compliant | A
WEB-CON-15 | Favorites | /en/favorites | Save/list | Compliant | A
WEB-CON-16 | KYC | /en/kyc | Upload 503 until AWS; manual review path | Compliant; RB-02/FD-02 | A/C/D
WEB-CON-17 | Localization | /{locale}/* | 1445-key parity, RTL/LTR, ar-EG formats | Compliant | A
WEB-CON-18 | UX states | all | Skeletons, empty, error+retry | Compliant | A
WEB-HST-01 | Host dashboard | /en/host | Actionable events | Compliant | A
WEB-HST-02 | Listings | /en/host/listings | List/draft/publish/edit | Compliant | A
WEB-HST-03 | Create listing | /en/host/listings/new | Full form | Compliant | A
WEB-HST-04 | Edit listing | /en/host/listings/{id}/edit | Edit + moderation outcome | Compliant | A
WEB-HST-05 | Photos | /en/host/listings/{id}/photos | Upload 503 until AWS; reorder/cover | Compliant; RB-02 | A/C
WEB-HST-06 | Availability | /en/host/listings/{id}/availability | Calendar rules/blocks | Compliant | A
WEB-HST-07 | Calendar | /en/host/calendar | Host calendar | Compliant | A
WEB-HST-08 | Booking requests | /en/host/bookings | Accept/reject, 24h expiry | Compliant | A
WEB-HST-09 | Earnings | /en/host/earnings | Earnings + payment activity | Compliant | A
WEB-HST-10 | Co-hosts | /en/host/listings/{id}/co-hosts | Co-host mgmt | Compliant | A
WEB-HST-11 | Host profile | /en/host/profile, /en/hosts/{id} | Edit + public page | Compliant | A
WEB-HST-12 | Host KYC | /en/host/kyc | Submit/status; upload blocked by RB-02 | A/C | A/C
WEB-HST-13 | Host reviews guest | booking detail | Host review form | Compliant | A
WEB-ADM-01 | Admin home | /en/admin | Ops overview | Non-benchmark | A
WEB-ADM-02 | KYC queue | /en/admin/kyc | Manual approve/reject | Compliant | A
WEB-ADM-03 | Moderation | /en/admin/pending | Listing queue | Compliant | A
WEB-ADM-04 | Payments | /en/admin/payments | Verify/reject proofs | Compliant | A
WEB-ADM-05 | Bookings | /en/admin/bookings | Read-only; cannot accept/reject | Compliant | A
WEB-ADM-06 | Disputes | /en/admin/disputes | Disputes + support replies | Compliant | A
WEB-ADM-07 | Staff | /en/admin/staff | Roles/permissions | Compliant | A
WEB-ADM-08 | Discovery | /en/admin/discovery | Non-benchmark ops | Non-benchmark | E
WEB-ADM-09 | Import | /en/admin/import | Listing import | Non-benchmark | E

## 06_FOUNDER_OBSERVATIONS
ID | Surface | Route | Current Behavior | Benchmark Status | Observation | Type | Decision Required? | Potential Impact | Status
WEB-OBS-001 | [8 empty] | OPEN
WEB-OBS-002 | [8 empty] | OPEN
WEB-OBS-003 | [8 empty] | OPEN
WEB-OBS-004 | [8 empty] | OPEN
WEB-OBS-005 | [8 empty] | OPEN
WEB-OBS-006 | [8 empty] | OPEN
WEB-OBS-007 | [8 empty] | OPEN
WEB-OBS-008 | [8 empty] | OPEN
WEB-OBS-009 | [8 empty] | OPEN
WEB-OBS-010 | [8 empty] | OPEN
WEB-OBS-011 | [8 empty] | OPEN
WEB-OBS-012 | [8 empty] | OPEN
WEB-OBS-013 | [8 empty] | OPEN
WEB-OBS-014 | [8 empty] | OPEN
WEB-OBS-015 | [8 empty] | OPEN

## 07_DIFFERENTIATION_IDEAS
ID | Founder Idea | Surface | Problem / Opportunity | Current StayOS Behavior | Benchmark Impact | Potential User Value | Dependencies | Technical Impact | Legal/Commercial Impact | Founder Decision | Implementation Status
DIFF-001 | [10 empty] | OPEN
DIFF-002 | [10 empty] | OPEN
DIFF-003 | [10 empty] | OPEN
DIFF-004 | [10 empty] | OPEN
DIFF-005 | [10 empty] | OPEN
DIFF-006 | [10 empty] | OPEN
DIFF-007 | [10 empty] | OPEN
DIFF-008 | [10 empty] | OPEN
DIFF-009 | [10 empty] | OPEN
DIFF-010 | [10 empty] | OPEN
GATE | Unlocked for code (0 implementable benchmark gaps). Ideas remain unimplemented until Founder Decision = APPROVED. Ideas depending on open FD-* decisions must note the dependency.

## 08_RELEASE_BLOCKERS
ID | Blocker | Evidence | Impact | Owner | Dependency | Priority | Status | Next Action
RB-01 | Real collection account + wallet destination | Placeholder values in config.py | Checkout unsafe for real money | Founder | Legal entity | P0 | OPEN | Founder supplies account → set PAYMENT_* vars
RB-02 | AWS storage (buckets+IAM+vars) for KYC/listings/payment-proof | AWS vars empty on Railway; S3_PAYMENT_PROOF_BUCKET undefined | Uploads 503; KYC/photos/proof blocked | Founder | AWS console access | P0 | OPEN | Create 3 buckets + CORS + scoped IAM in me-central-1; set vars on API+worker
RB-03 | Payment processor decision | FD-01 conflict | Online payments undefined | Founder | FD-13 entity | P0 | OPEN | Decide in 04_FOUNDER_DECISIONS
RB-04 | Legal entity + marketplace characterization | No entity data | Gates RB-01/RB-03/RB-06/RB-07 | Founder+counsel | Counsel | P0 | OPEN | Engage Egyptian counsel
RB-05 | CBE PSP/PSO analysis | Manual collection of guest funds; CBE PSP rules June 2025 (Banking Law 194/2020), ~June 2026 transition | May require licensing/structure | Counsel | FD-13 | P0 | OPEN | Counsel opinion; do not self-interpret
RB-06 | PDPL compliance | Exec Regs Decree 816/2025 in force; deadline 2026-11-01; KYC/biometric-adjacent data | License/permit, DPO, transfer rules may apply | Counsel | FD-13 | P0 | OPEN | Counsel gap assessment before deadline
RB-07 | Tourism licensing characterization | Hotel & Tourist Establishments Law 8/2022 covers accommodation units | Host/platform licensing scope unclear | Counsel | FD-13 | P1 | OPEN | Counsel to confirm applicability to platform vs hosts
RB-08 | KYC-ML architecture | Textract/Rekognition absent in me-central-1 | Automated KYC blocked; manual works | Founder | FD-02 | P1 | OPEN | Decide FD-02
RB-09 | Akedly OTP live delivery | Provider integrated; unverified live | Real-user signup/verify blocked | Founder/Eng | Provider account | P0 | OPEN | Send test OTP on deployed env
RB-10 | ENVIRONMENT=production | Dev-token reachable (dev implied) | Dev Login must not reach public | Eng | Prod domain | P1 | OPEN | Flip at launch
RB-11 | Production domain + CORS | Preview only; no prod domain | Public URL undefined | Founder | Domain purchase | P1 | OPEN | Buy domain; set CORS_ORIGINS
RB-12 | Google Maps var + rotation | Malformed 'GoogleـMapsـAPI' name on worker/beat; rotation unconfirmed after historical literal leak | Maps on workers; key hygiene | Founder/Eng | GCP console | P1 | OPEN | Fix var name; confirm rotation
RB-13 | Sentry DSN | Code present; DSN unset | No error monitoring | Eng | Sentry project | P2 | OPEN | Set SENTRY_DSN
RB-14 | Backups | Not verified | Data-loss risk | Eng | Railway/db backups | P1 | OPEN | Enable backup schedule
RB-15 | Mobile: OPPO booking CTA + map/list toggle | Physical device P0s | Mobile acceptance blocked | Eng | FD-11 | P1 | OPEN | Diagnose TouchableOpacity; rebuild preview
RB-16 | Mobile framework ADR | DEC-014 pending; ADR-016 number collision | Mobile implementation gated | Founder | FD-11 | P1 | OPEN | Decide FD-11; commit ADR under free number
RB-17 | Store credentials/signing | Unknown | Distribution blocked | Founder | FD-11 | P2 | OPEN | Provision accounts/signing
RB-18 | e-invoice/e-receipt (ETA) applicability | ETA e-invoice Dec.188/2020 + eReceipt B2C | Possible fiscal integration | Accountant | FD-13 | P1 | OPEN | Accountant to confirm scope

## 09_INFRASTRUCTURE
Component | State | Detail / Evidence
Railway project | ACTIVE | stayos-demo · fcfb039d-bf12-4bb9-8434-98de4742c4cf · env production 841e69f7
API service | SUCCESS @ 2f602b0 | stayos-demo · deployment ae8267c4 · domain stayos-demo-production.up.railway.app
Worker | SUCCESS @ 2f602b0 | deployment b5c774f4
Beat | SUCCESS @ 2f602b0 | deployment 55b95446
Postgres | RUNNING | Railway-managed; PostGIS
Redis | RUNNING | Railway-managed
Vercel | PREVIEW ONLY | project web · preview stayos-814l6q390-islam-elbaz-s-projects.vercel.app · no prod domain
AWS/S3 | UNCONFIGURED | vars empty; buckets/ IAM not created; do not create without founder
Terraform | PRESENT, not applied | Railway arch differs; do not run terraform apply
CI/CD | Push→auto-deploy | product-completion-review → Railway + Vercel preview; railway_deploy_guard.sh for manual

## 10_SECURITY
Item | Status | Evidence / Action
RBAC + ownership | VERIFIED | 89 authz/security tests pass; admin cannot accept/reject bookings
Upload safety | VERIFIED | MIME allowlists + storage-config 503 guards on all 3 presign paths (3129415, 8994f6d)
CORS | VERIFIED | Project-scoped regex (418dca8)
KYC gating | VERIFIED | Host upgrade requires reviewed KYC doc (ae490e0)
Dev-token exposure | KNOWN ISSUE | Reachable on deployed env — required for acceptance; must be production-gated at launch (RB-10)
Google Maps key | OPEN | Malformed var name on worker/beat; rotation after historical leak unconfirmed (RB-12)
Secrets in repo | CLEAN | No secrets committed; workbook is names-only
Rate limiting/audit | PRESENT | security/rate_limit.py, audit.py, PII module
Payment-proof bucket | MISSING VAR | S3_PAYMENT_PROOF_BUCKET undefined on Railway (RB-02)

## 11_DATABASE
Item | Value
Engine | PostgreSQL + PostGIS (Railway)
ORM/migrations | SQLAlchemy async + Alembic
Head | 040_candidate_governorate
Version count | 41
Head check | alembic heads → single head (verified 2026-09-20)
Seeds | seed_acceptance*.py — guest/host/staff/admin + Zamalek+Maadi listings

## 12_API
Item | Value
Framework | FastAPI modular monolith (src/app)
OpenAPI paths | 156 (regenerated 2026-09-20; includes reviews q param)
Docs | /docs Swagger · /openapi.json
Modules | auth, availability, bookings, discovery, disputes, favorites, finance, host, importer, kyc, listings, locations, messages, notifications, operations, payments, reservations, reviews, security
Realtime | SSE + Redis pub/sub (ADR-008/DEC-014)
Async | Celery worker + beat (expiry tasks, notifications, automations)

## 13_TESTS
Suite | Result | When / Command
Backend full | 1160 passed · 80.60% cov | 2026-09-20 · python3 -m pytest
Auth/security | 89 passed | pytest test_auth.py test_auth_otp_akedly.py test_security.py
Frontend typecheck | PASS | npm run type-check
Frontend lint | PASS (pre-existing warnings) | npm run lint
Vitest | 12/12 | npm test
Production build | PASS | npm run build
Mobile typecheck | PASS | apps/mobile npx tsc --noEmit
OpenAPI drift | NONE | npm run generate:api regenerated w/ q param
Migrations | single head | alembic heads

## 14_DEPLOYMENTS
Service | Deployment ID | Commit | Status | Created
API | ae8267c4-b9d2-4b3f-bc13-d5ea54c856e5 | 2f602b0 | SUCCESS | 2026-09-20T00:40:42Z
Worker | b5c774f4-23a7-4b12-af23-9d151bc55e6a | 2f602b0 | SUCCESS | 2026-09-20T00:40:42Z
Beat | 55b95446-3543-4a92-a366-f000e3366a36 | 2f602b0 | SUCCESS | 2026-09-20T00:40:42Z
Vercel | preview | 2f602b0 | LIVE (preview) | on push

## 15_MOBILE_READINESS
Item | State | Detail
GATE STATEMENT | GATED | Mobile implementation is gated on Founder Web Acceptance and resolution of relevant Founder Decisions.
Architecture | Expo ~51 / RN 0.74.5 | com.stayos.mobile iOS+Android; owner islamelbaz; EAS 04b13a13
Build profile | preview only | internal Android APK; latest builds incl. 84050149, 8c8352e9, 9d4c1255
Typecheck | PASS | tsc --noEmit clean (2026-09-20)
Physical device | 2 open P0s | OPPO CPH2481 Android 15: booking CTA احجز الآن no navigation; search map/list toggle dead
Framework decision | OPEN (FD-11) | DEC-014 pending; ADR-016 number collision; DEC-018 postpones native until 100+ bookings
API compatibility | COMPATIBLE | same REST API; KYC content-type defaults preserve client contract (8994f6d)
Localization | PARITY REQUIRED | ar/en required on mobile before freeze
Signing/store | UNKNOWN | no store credentials verified
UX freeze | NOT FROZEN | web founder acceptance may change behavior — mobile requirements freeze afterward

## 16_LEGAL_ACCOUNTING
Item | Classification | Detail | Source / Action
Legal entity / legal form | FOUNDER DECISION | Form, name, CR, tax card, HQ, activity code required | Dossier inputs; counsel
Commercial registration | LEGAL COUNSEL TO CONFIRM | GAFI incorporation route | gafi.gov.eg
Tax registration / VAT | ACCOUNTANT TO CONFIRM | Registration + VAT applicability to commission/fees | eta.gov.eg
e-invoice / e-receipt | ACCOUNTANT TO CONFIRM | eInvoice (Dec.188/2020); eReceipt B2C integration scope | sdk.invoicing.eta.gov.eg
Marketplace characterization | LEGAL COUNSEL TO CONFIRM | Platform vs merchant-of-record; who invoices guest | Counsel — do not self-interpret
Payment collection flow / money custody | LEGAL COUNSEL TO CONFIRM | Guest pays StayOS-controlled account → host net; custody characterization | Counsel
CBE PSP/PSO licensing | LEGAL COUNSEL TO CONFIRM | CBE licensing rules (June 2025, Banking Law 194/2020); Category A/B; ~June 2026 transition | cbe.org.eg
Tourism licensing | LEGAL COUNSEL TO CONFIRM | Hotel & Tourist Establishments Law 8/2022 covers 'accommodation units'; platform vs host scope | mota.gov.eg
Consumer protection | LEGAL COUNSEL TO CONFIRM | CPA Law 181/2018 disclosures/refunds alignment | cpa.gov.eg
PDPL | LEGAL COUNSEL TO CONFIRM | Law 151/2020 + Exec Regs Decree 816/2025 (in force Nov 2025); compliance deadline 2026-11-01; controller/processor license, DPO, transfer approvals | mcit.gov.eg / PDPC
KYC / biometric-adjacent data | LEGAL COUNSEL TO CONFIRM | ID images + selfies are sensitive-category-adjacent; ML region choice matters | Counsel + FD-02
Contracts / ToS / privacy / host terms | LEGAL COUNSEL TO CONFIRM | Not yet drafted in repo | Counsel
Refund/cancellation legal alignment | LEGAL COUNSEL TO CONFIRM | Approved rules (5-day processing etc.) need ToS alignment | Counsel
IP / trademark | LEGAL COUNSEL TO CONFIRM | StayOS mark; Airbnb-proprietary assets not copied | Counsel
Employment/contractor (staff/co-hosts) | LEGAL COUNSEL TO CONFIRM | Staff roles exist in product | Counsel
Hosting/transfer of personal data | TECHNICAL IMPLEMENTATION ITEM | AWS region choice + PDPL transfer approval interact | FD-02 + counsel

## 17_MANUAL_ACTIONS
Grp | Action | Owner | Why | Status
A | Supply real bank + Vodafone Cash account → PAYMENT_* vars | Founder | Checkout real money | OPEN
A | AWS me-central-1: create KYC/listings/private-proof buckets + CORS + scoped IAM → set vars on API+worker | Founder | Unblocks all uploads | OPEN
A | Decide FD-01 processor + FD-02 KYC-ML | Founder | Payment/KYC architecture | OPEN
A | Register legal entity + engage Egyptian counsel | Founder | All regulated items | OPEN
A | Set ENVIRONMENT=production at launch | Eng/Founder | Disable dev login | OPEN
B | Fix malformed Maps var; confirm key rotation | Eng | Worker maps + hygiene | OPEN
B | Add S3_PAYMENT_PROOF_BUCKET, META_*, SENTRY_DSN | Eng | Proof storage + monitoring | OPEN
B | Verify Akedly OTP delivers live | Eng | Real-user auth | OPEN
B | Enable backups | Eng | Data safety | OPEN
B | Production domain + CORS_ORIGINS | Founder | Public launch | OPEN
C | SES SigV4 signing; auto-migrate on deploy; no terraform apply for Railway arch | Eng | Hygiene | OPEN
D | Paymob outreach; refund-calc function; channel integrations | Founder | Deferred per DEC-018 | OPEN

## 18_CREDENTIAL_SAFE_HANDLING
Rule | Detail
No secrets in workbook/repo | Names and states only — never values
Where secrets live | Railway variables / provider consoles / founder password manager
Rotation | Google Maps key rotation unconfirmed — confirm in GCP console, update vars, do not paste values here
Sharing | Send credentials via founder-approved secret channel only; never chat/email/plain files
Test access | Use Dev Login + seeded accounts; no static passwords recorded
Signing/store credentials | Founder-controlled; record existence only

## 19_OFFICIAL_SOURCES
Authority | URL | Relevance
Central Bank of Egypt | https://www.cbe.org.eg | PSP/PSO licensing rules (June 2025); Banking Law 194/2020
Egyptian Tax Authority | https://eta.gov.eg | Tax registration, VAT, e-invoice/e-receipt
ETA eInvoicing SDK | https://sdk.invoicing.eta.gov.eg | e-invoice/e-receipt integration docs
GAFI | https://www.gafi.gov.eg | Incorporation / commercial registry
ITIDA | https://www.itida.gov.eg | Tech company registration / export programs
Ministry of Tourism & Antiquities | https://www.mota.gov.eg | Hotel & Tourist Establishments Law 8/2022; licensing categories
MCIT | https://mcit.gov.eg | PDPL executive regulations; PDPC supervision
Consumer Protection Agency | https://cpa.gov.eg | CPA Law 181/2018
Airbnb (product benchmark) | https://www.airbnb.com | Behavioral benchmark only — no proprietary assets
Railway docs | https://docs.railway.com | Infra ops

## 20_CHANGELOG
Date | Change | By
2026-09-20 | Workbook created (release review master) after benchmark closure 0d2b14e/2f602b0 | Devin
2026-09-20 | Founder Decision Register + Web Acceptance Register created under docs/release/ | Devin
2026-09-20 | PDPL Exec Regs (816/2025) + CBE PSP rules (June 2025) verified from official/current sources | Devin