## README
Item | Value / Instruction
Workbook purpose | Technical handoff / review workbook for StayOS before public launch and mobile completion.
Prepared | 20 Sep 2026
Important security rule | Do NOT store production passwords, API keys, AWS secrets, database passwords, OTP secrets, private tokens or recovery codes in this workbook.
Safe test credentials | Use Dev Login / seeded acceptance accounts where available. Static passwords are intentionally not recorded because current acceptance auth uses environment-gated Dev Login.
Core benchmark | Airbnb 1:1 behavioral/product-depth benchmark; no cloning of branding, code, proprietary assets or architecture.
Main branch | Must remain untouched during review unless explicitly approved.
Current engineering branch | product-completion-review
Latest known KYC hardening commit | 8994f6d
Backend tests | 1155 passed; coverage 80.58%
Frontend checks | Typecheck ✓, lint ✓ (pre-existing warnings), Vitest 12/12 ✓, production build ✓
Current KYC limitation | AWS S3 storage variables are not configured on Railway; live initiate returns 503 until AWS is manually provisioned.
Current KYC architecture decision | Manual review is viable; automated Textract/Rekognition region/provider decision remains open.
How to use | Start with URLs → Environments → Architecture → Roles/Test Accounts → Deployment → Manual Actions → Release Checklist.

## URLs
Category | Name | URL | Environment | Status | Notes
Web | Vercel Preview (latest known) | https://stayos-814l6q390-islam-elbaz-s-projects.vercel.app/en | Preview | Known | SSO protected; latest known preview from KYC deployment.
API | Railway API | https://stayos-demo-production.up.railway.app | Staging/Live backend | Known | FastAPI backend endpoint; exact public launch topology to be re-confirmed.
Admin | Admin UI | https://stayos-814l6q390-islam-elbaz-s-projects.vercel.app/en/admin | Preview | Known | Requires authorized admin/dev login.
Auth | Login | https://stayos-814l6q390-islam-elbaz-s-projects.vercel.app/en/auth/login | Preview | Known | Dev Login is environment-gated.
KYC | Guest KYC | https://stayos-814l6q390-islam-elbaz-s-projects.vercel.app/en/kyc | Preview | Known | Requires guest authentication; storage currently unconfigured.
Repo | GitHub repository | TO BE FILLED BY DEVIN | Source | Open | Do not invent. Devin should populate canonical repo URL.
Deploy | Vercel project | TO BE FILLED BY DEVIN | Hosting | Open | Canonical project dashboard URL.
Deploy | Railway project | TO BE FILLED BY DEVIN | Hosting | Open | Canonical project/service URLs and project ID.
Cloud | AWS account/console | https://console.aws.amazon.com/ | AWS | Known | Current console identity had Access Denied for required setup actions.
Tax | Egyptian Tax Authority | https://eta.gov.eg/en/home | Egypt | Official | Tax/e-invoice/e-receipt reference.
Corporate | GAFI | https://gafi.gov.eg/ | Egypt | Official | Company incorporation/post-incorporation.
Registry | ITDA Commercial Registry | https://www.itda.gov.eg/en/sgl-en.html | Egypt | Official | Commercial Registry laws and procedures.
Privacy | PDPC | https://www.pdpc.gov.eg/ | Egypt | Official | PDPL + Executive Regulations 816/2025.
Tourism | Ministry of Tourism | https://mota.gov.eg/ | Egypt | Official | Tourism/hotel licensing reference.

## Environments
Environment | Component | Provider | Endpoint / Region | Deployment Source | Health / Status | Notes
Preview | Web | Vercel | stayos-*.vercel.app | product-completion-review | Accessible | SSO protected.
Staging/Backend | API | Railway | stayos-demo-production.up.railway.app | Railway service | Healthy at last verification | CORS fixed for project-specific Vercel preview origins.
Staging/Backend | Worker | Railway | same project | Railway service | Healthy at last verification | Celery worker processes async KYC; ML unavailable keeps documents pending.
Staging/Backend | Beat | Railway | same project | Railway service | Needs periodic health confirmation | Celery scheduler.
Database | PostgreSQL/PostGIS | Railway / local | Exact DB URL must NOT be exported | Deployment-specific | Active | Never place password in workbook.
Cache/Queue | Redis | Railway / local | Exact URL must NOT be exported | Deployment-specific | Active | Never place password in workbook.
KYC storage | AWS S3 | AWS | me-central-1 | Manual setup pending | NOT CONFIGURED | Bucket/IAM/credentials pending; do not Terraform apply blindly.

## Architecture
Layer | Technology / Component | Role | Known Details | Review Status | Developer Notes
Web | Next.js / React | Guest/Host/Admin UI | apps/web; Arabic/English; RTL/LTR; React Query used for invalidation/state. | Known | Verify exact package versions from package.json.
API | FastAPI | REST backend | API namespace /api/v1; OpenAPI generated types used by web. | Known | Verify exact version from pyproject/lockfile.
Async | Celery | Background jobs | KYC worker and scheduled jobs. | Known | Inspect queue names and retry policies.
Database | PostgreSQL + PostGIS | Primary relational DB + geospatial | Booking, listings, users, payments, reviews, KYC, etc. | Known | Verify current migration head and production migration procedure.
Cache/Queue | Redis | Celery broker/cache | Used locally and in staging. | Known | Verify persistence/eviction expectations.
Storage | AWS S3 | KYC documents/images | Presigned browser upload; MIME type signed per file. | Partial | Bucket currently not provisioned on Railway; CORS spec documented.
Maps | Leaflet + OSM + Nominatim | Web maps/search | Web uses Leaflet/OSM/Nominatim; Google Places is server-side Supply Discovery. | Known | Verify attribution and rate-limit/commercial-use compliance.
Supply Discovery | Overpass OSM + Google Places | Admin supply discovery | Latest known 55 candidates: 50 OSM + 5 Google Places; count can change by provider/query. | Known | Re-run before launch and document provider terms.
Mobile | React Native / Expo | Android/iOS client | apps/mobile; Android/iOS completion pending. | In progress | Final mobile release audit must be separate before public launch.

## Roles_Test_Accounts
Role | Account / Identifier | Login Method | Username / Identifier | Password | KYC | Purpose | Status | Notes
Guest | Acceptance Guest | Dev Login | seed-accept-gues-0000-000000000001 | N/A — no static password | VERIFIED | Primary acceptance booking tests | Ready | Use Login as Guest; do not turn this account into Host.
Host | Omar Hassan | Dev Login | Seed host account / exact ID to be filled by Devin | N/A — no static password | VERIFIED | Request-to-book + Instant Book host testing | Ready | Has Request-to-Book and Instant Book listings.
Admin | Admin test account | Dev Login / exact mechanism to verify | TO BE FILLED BY DEVIN | DO NOT STORE | N/A | Admin queue/operations/security tests | Open | Never store admin production password.
Production | Production users | Real auth | NOT FOR WORKBOOK | DO NOT STORE | Varies | Public users | Not launched | Use password manager/secret manager.

## Seed_Data
Entity | Identifier | Name | Role/Type | Location | Price | Cleaning Fee | Key Attributes | Photos | Status | Notes
User | seed-accept-gues-0000-000000000001 | Acceptance Guest | Guest | Egypt | — | — | KYC VERIFIED | — | Ready | Primary guest acceptance fixture.
User | seed-host-0000-0000-000000000002 | Omar Hassan | Host | Egypt | — | — | KYC VERIFIED; Arabic/English/French | — | Ready | Host acceptance fixture.
Unit | seed-unit-0001-0000-000000000001 | Chic Nile View Apartment | Request-to-Book | Zamalek, Cairo | 1500 EGP/night | 200 EGP | 2BR / 3 beds / 2 bath / 4 guests; pets; self check-in; moderate cancellation | 5 | Ready | Seed acceptance listing.
Unit | seed-unit-0002-000000000002 | Modern Garden Apartment | Instant Book | Maadi, Cairo | 2000 EGP/night | 300 EGP | 3BR / 4 beds / 2 bath / 6 guests; pets; self check-in; flexible cancellation | 5 | Ready | Seed acceptance listing.

## API_Reference
Area | Method | Path / Pattern | Auth / Permission | Purpose | Status | Notes
Health | GET | /api/health | Public/health | Service health | Known | Confirm exact deployment route.
Auth | GET | /api/v1/auth/me | Authenticated | Current user/session | Known | Use to verify Dev Login target.
KYC | POST | /api/v1/kyc/initiate | KYC-eligible guest | Create KYC doc + presigned URLs | Known | Currently returns 503 until AWS storage config exists.
KYC | POST | /api/v1/kyc/documents/{id}/submit | Document owner | Submit KYC document for review | Known | ML failure leaves document pending.
KYC | GET | /api/v1/kyc/pending | Staff KYC permission | Admin/staff pending queue | Known | Manual review path.
Payments | GET | /api/v1/payments/host | Host/Admin | Host payment activity | Known | Route shadowing was fixed.
Host bookings | GET | /api/v1/host/bookings | Host/Admin GET | Host booking inbox | Known | Server-side filters/pagination.
Bookings | PATCH | booking update endpoint | Owner/cohost for accept/reject | Booking lifecycle actions | Known | Admin accept/reject explicitly blocked.

## DB_Migrations
Migration / Area | Known State | Verification Needed | Manual Action | Risk
Current migration head | 040 at latest known infrastructure closure | Verify deployed DB head | Run read-only migration status first | High
030 Payment cleaning fee | Fixed schema target to payment | Verify production/staging applied | Do not run production migration without approved process | High
033 KYC/listing expansion | Applied locally/non-prod in prior work | Verify deployed DB | Use controlled deployment migration procedure | High
038 Instant Book | Added instant_book | Verify deployed DB | Controlled migration only | High
040 latest known head | Current from latest closure | Verify Railway DB | Document before mobile release | High

## Security
Area | Finding / Requirement | Current State | Action | Owner | Priority
Secrets | Production/API/AWS credentials must not be stored in repo or workbook | Not exported | Use Railway/Vercel/AWS secret manager/password manager | Founder/DevOps | Critical
AWS Google Maps key | Historical key was found in git history | Not yet rotated per founder instruction | Rotate/restrict after all current engineering changes are complete | Founder/DevOps | High
KYC AWS | S3 variables empty on Railway | Not configured | Manual AWS batch after engineering closure | Founder/DevOps | Critical
KYC ML | Textract/Rekognition unavailable in canonical me-central-1 | Architecture decision open | Legal/data-residency + architecture decision | Founder/Legal/Architect | High
CORS | Vercel origin regex narrowed to StayOS project | Fixed | Keep exact project-scoped policy | Developer | Medium
Admin RBAC | Admin cannot accept/reject host booking requests | Hardened | Retest after major changes | Developer/QA | High
PDPL | KYC contains identity/biometric-sensitive data | Compliance work required | Data map, DPA, retention, DPO assessment | Legal/Privacy | Critical

## Manual_Actions
Order | Action | Where | Exact Steps | Dependency | Status | Do Not Do
1 | Confirm legal entity/activity | Lawyer/Accountant | Choose legal form + exact activity/object; determine marketplace/tourism licensing position. | Legal counsel | Open | Do not launch publicly before this is resolved.
2 | AWS KYC setup | AWS Console | Create staging KYC S3 bucket in me-central-1; block public access; versioning; SSE-S3; apply approved CORS; create least-privilege credentials. | AWS root/admin | Open | Do not use Terraform apply blindly.
3 | Railway KYC variables | Railway | Set AWS_REGION, S3_KYC_BUCKET, AWS_ACCESS_KEY_ID, AWS_SECRET_ACCESS_KEY on API + worker only. | AWS setup | Open | Never paste secrets into chat/workbook.
4 | Rotate historical Google key | Google Cloud | Restrict/rotate old key after engineering work is stable; update only intended mobile configuration. | Engineering closure | Deferred | Do not rotate mid-sprint unless emergency.
5 | Mobile release credentials | Google Play / Apple | Verify app identifiers, signing, bundle IDs, store accounts, privacy URL, support URL, release certificates. | Mobile completion | Open | Do not put signing keys in workbook.
6 | Tax onboarding | ETA | Confirm tax registration, VAT/e-invoice/e-receipt applicability and onboarding requirements. | Legal entity + accountant | Open | Do not assume VAT treatment.
7 | Trademark/IP | ITDA/IP counsel | Search StayOS mark/name, domain ownership, copyright/software deposit strategy, contractor IP assignments. | Legal counsel | Open | Do not assume trademark availability.

## Release_Checklist
Area | Gate | Evidence | Status | Owner | Blocking? | Notes
Product | Guest discovery → listing → booking → stay → review end-to-end | E2E evidence + manual acceptance | Open | QA | Yes | Airbnb behavioral benchmark; no invented requirements.
Product | Host Request-to-Book + Instant Book | Seed fixtures + acceptance runs | Open | QA | Yes | Both booking modes tested previously.
Product | Admin operations/RBAC | Security matrix tests | Mostly complete | Developer | Yes | Admin accept/reject must remain blocked.
Payments | Real provider integration | Provider decision + production integration | Open | Founder | Yes | Current flow is manual proof; Paymob/Stripe unresolved.
KYC | Storage + manual review | AWS storage + upload + admin review | Open | Founder/DevOps | Yes | Current app code supports manual pending flow.
Mobile | Android | Release candidate + store test | In progress | Mobile | Yes | Final app audit pending.
Mobile | iOS | Release candidate + TestFlight | In progress | Mobile | Yes | Final app audit pending.
Legal | Entity + activity + tourism determination | Signed counsel memo / registrations | Open | Legal | Yes | Must be resolved before public launch.
Tax | Tax/e-invoice/e-receipt | Accountant sign-off | Open | Accountant | Yes | Depends on actual money flow.
Privacy | PDPL/KYC assessment | Counsel/privacy sign-off | Open | Legal | Yes | KYC is sensitive/biometric-related.
Security | Secrets/keys rotation and restrictions | Cloud provider evidence | Open | DevOps | Yes | Do after current engineering closure.

## Official_Sources
Topic | Authority | Official URL | What It Supports | Last Checked
Companies Law | GAFI | https://gafi.gov.eg/en/contenttemplate/ad17cbdb-f2cd-4521-ad97-78d0fae50ec8 | Law 159/1981 corporate framework | Sep 2026
Electronic incorporation | GAFI | https://gafi.gov.eg/ar/contenttemplate/ca1b9d8b-76d1-46dc-a677-eb4ba5ccaae3 | Electronic company establishment information | Sep 2026
Commercial Registry | ITDA | https://www.itda.gov.eg/en/sgl-en.html | Registry law/procedures | Sep 2026
Tax / e-invoice | ETA | https://eta.gov.eg/en/home | Tax and electronic invoice/receipt framework | Sep 2026
Personal Data | PDPC | https://www.pdpc.gov.eg/ | PDPL 151/2020 + Executive Regulations 816/2025 | Sep 2026
Social insurance | NOSI | https://www.nosi.gov.eg/ar/Services/Pages/Info/ANewEmployerFile.aspx | Employer file and employee insurance process | Sep 2026
Tourism licensing | MOTA | https://mota.gov.eg/ar/%D8%A7%D9%84%D8%AE%D8%AF%D9%85%D8%A7%D8%AA-%D8%A7%D9%84%D8%B1%D9%82%D9%85%D9%8A%D8%A9/%D8%A7%D9%84%D8%B4%D8%B1%D9%83%D8%A7%D8%AA-%D9%88%D8%A7%D9%84%D9%85%D9%86%D8%B4%D8%A2%D8%AA-%D8%A7%D9%84%D9%81%D9%86%D8%AF%D9%82%D9%8A%D8%A9-%D9%88%D8%A7%D9%84%D8%B3%D9%8A%D8%A7%D8%AD%D9%8A%D8%A9/%D8%AA%D8%B1%D8%A7%D8%AE%D9%8A%D8%B5-%D8%B4%D8%B1%D9%83%D8%A7%D8%AA-%D8%A7%D9%84%D8%B3%D9%8A%D8%A7%D8%AD%D8%A9/ | Tourism company licensing track; exact StayOS applicability must be determined | Sep 2026
Software/IP | GAFI/ITDA | https://www.gafi.gov.eg/English/StartaBusiness/Laws-and-Regulations/Documents/IntellectualPropertyRightsLaw.pdf | Copyright/software protection reference | Sep 2026

## Credentials_SafeHandling
Credential Type | Example / Account | Where It Should Live | Workbook Value | Reason
Dev test login | Acceptance Guest / Host | App Dev Login | No password; use Dev Login | Current acceptance setup uses environment-gated Dev Login.
Railway API secrets | AWS / DB / Redis / other | Railway Variables | DO NOT STORE | Secrets should remain in provider secret store.
Vercel secrets | App env vars | Vercel Project Settings | DO NOT STORE | Never export secrets into Excel.
AWS access key | Railway KYC IAM credential | Railway Variables / secret manager | DO NOT STORE | Least privilege; never chat/email/export.
Google API keys | Places/Maps | Google Cloud + provider secret/config | DO NOT STORE | Restrict by API/application; rotate after current work.
App signing keys | Android/iOS | Google Play/Apple/secure local secret store | DO NOT STORE | Loss/compromise can block release or expose signing.