## Slide 1
MANAGEMENT SITUATION
StayOS — Before vs After the Product Version Audit
What we agreed to build • What actually got built • What the audit changed • What is NOT cancelled
14 August 2026

## Slide 2
EXECUTIVE CONCLUSION
The audit did not cancel the supply strategy — it changed the priority of execution.
WHAT WE AGREED
Build a supply-acquisition path that can discover property candidates from public sources, import/seed them, and use owner outreach to convert them into real StayOS inventory.
WHAT GOT BUILT
Discovery Engine + CSV/Excel importer + owner outreach flow are now part of the product/tooling. Discovery is explicitly classified as a supply-activation admin tool.
WHAT THE AUDIT CHANGED
The bottleneck is no longer 'build supply tooling'. It is deployment + real host acquisition + real bookings. The next step is execution, not another supply feature.
BOTTOM LINE
Nothing important from the supply plan was cancelled. Some items were reclassified: the discovery engine is V1-enabling tooling; unclaimed-listing/claim UX is deferred to V2; real owner recruitment is now a management execution task.
StayOS • Management Situation • 14 Aug 2026

## Slide 3
WHAT WE WERE WORKING TOWARD
Supply acquisition was never just 'scrape listings and publish them'.
1. DISCOVER
Find property candidates from public sources / maps / directories.
2. NORMALIZE
Clean, score and deduplicate candidates.
3. IMPORT / SEED
Bring candidate data into StayOS through the admin importer.
4. CONTACT OWNER
Use outreach to identify the real owner/operator and invite them.
5. VERIFY + ONBOARD
Owner provides/validates data, KYC and listing details; admin approves.
6. LISTED
Only then does the unit become real StayOS supply.
StayOS • Management Situation • 14 Aug 2026

## Slide 4
WHAT ACTUALLY GOT BUILT
Evidence from the 14 Aug Product Version Audit
Capability | Current state | Management meaning
Discovery Engine | Code complete; admin surface exists | READY as a supply-activation tool
OSM / Google Places adapters | Implemented interfaces | Can generate property candidates
Scoring / deduplication | Implemented | Reduces duplicate / low-quality candidates
CSV / Excel importer | Code complete | Bulk seed path exists
Owner outreach template | Implemented in P0 work | Converts candidates into conversations
Listing lifecycle | PENDING → REVIEW → LISTED | Verification remains a gate
Real supply acquisition | 0 real listings / 0 hosts | NOT STARTED operationally
StayOS • Management Situation • 14 Aug 2026

## Slide 5
WHAT CHANGED AFTER THE AUDIT
The biggest change is priority, not product direction.
Before / working assumption | After audit | Decision
More supply tooling may be needed | Supply tooling is already sufficient for alpha | STOP adding supply features
Build toward a polished marketplace | Core booking loop is code-complete | MOVE to deployment + real use
Internet discovery is a product feature | Discovery is an admin supply-activation tool | KEEP, but do not overbuild
Unclaimed listings / claim UX | Useful, but explicitly deferred | WAIT for V2
Need to prove the marketplace | Need real hosts, listings, bookings, payouts, NPS | START now
MANAGEMENT SHIFT
Engineering → Operations / Commercial Validation
StayOS • Management Situation • 14 Aug 2026

## Slide 6
THE IMPORTANT DISTINCTION: CANDIDATE ≠ LISTING
This is the point most likely to be forgotten after the audit.
PUBLIC-WEB CANDIDATE
A discoverable property/place found through OSM, Google Places, or other permitted public sources. Useful for finding supply. Not yet a verified StayOS listing.
OWNER / OPERATOR
Candidate is converted through outreach, owner participation, accurate data, KYC and listing approval. This is the commercial step that has NOT started.
LIVE STAYOS LISTING
Verified listing approved by admin and suitable for guests to search and book. V1 requires real supply, not just discovered candidates.
Management interpretation: the internet-discovery engine remains valid, but it is an acquisition instrument — not permission to publish third-party inventory as if it were owner-approved supply.
StayOS • Management Situation • 14 Aug 2026

## Slide 7
SUPPLY WORK: DONE vs REMAINING
The gap moved from software to execution.
Workstream | Done? | Remaining
Discovery / candidate generation | YES | Run it against real sources and review candidates
Normalization / dedup / scoring | YES | Operationally use the output
Bulk import | YES | Seed actual candidate inventory
Owner outreach | TOOL READY | Founder must contact owners
Owner participation / claim | NO | Commercial conversion
KYC + listing completion | YES (workflow) | Run with real hosts
Admin approval → LISTED | YES (workflow) | Process real units
40+ New Cairo live listings | NO | MVP Gate requirement
StayOS • Management Situation • 14 Aug 2026

## Slide 8
WHY THIS MATTERS FOR V1
The audit redefined the finish line as operating proof, not code completeness.
V1 / MVP GATE
• 40+ live listings in New Cairo • 7+ completed bookings • EGP payment collected • 5+ host payouts • 0 fraud incidents • Guest NPS ≥ 50 • Host NPS ≥ 50 • Operations playbook • Ops hire identified
WHAT THIS MEANS FOR SUPPLY
The Discovery Engine is not the goal. The goal is to turn candidates into verified, bookable inventory. Therefore: 1. Run discovery. 2. Contact owners. 3. Onboard hosts. 4. Publish verified listings. 5. Track bookings. No new discovery architecture is justified now.
StayOS • Management Situation • 14 Aug 2026

## Slide 9
WHAT WAS NOT CANCELLED — ONLY MOVED
The audit explicitly protects scope discipline.
Item | Current placement | Status
Discovery Engine | V1 / supply activation | KEEP
CSV / Excel bulk import | V1 / supply activation | KEEP
Owner outreach | V1 operations | DO NOW
Unclaimed listing + claim workflow | V2 | WAIT
Duplicate automation enhancements | V2 | WAIT
Map-based search | V2 | WAIT
Egyptian wallet payments | V2 | WAIT
Reviews & Ratings | V2 | WAIT
Mobile / messaging / scale tooling | V3+ | WAIT
StayOS • Management Situation • 14 Aug 2026

## Slide 10
CURRENT MANAGEMENT SITUATION — 14 AUG 2026
The project is at the threshold between code completion and real-world operations.
V1 STATUS: YELLOW
CURRENT STAGE: Code-Complete Pre-Alpha
PRODUCT: Core booking loop code-complete
TECHNOLOGY: Deployment-ready, environment not provisioned
COMMERCIAL: 0 hosts / 0 listings / 0 bookings
VALIDATION: 0 real-world users
CRITICAL BLOCKER: No running environment + no real credentials
NEXT GATE: Closed Alpha → first real host + first real listing + first real guest
StayOS • Management Situation • 14 Aug 2026

## Slide 11
CRITICAL PATH — WHAT WE SHOULD DO NOW
Shortest path to the next meaningful gate.
1
Provision environment
No users can operate until the platform is live.
2
Configure real credentials
Prove OTP, storage, KYC and notifications against real services.
3
Run live smoke test
Move from code confidence to environment confidence.
4
Run discovery + recruit hosts
Turn candidates into verified New Cairo supply.
5
Publish first real listings
Start the marketplace with real inventory.
6
Acquire first guests + bookings
Generate the evidence that the product actually works.
StayOS • Management Situation • 14 Aug 2026

## Slide 12
MANAGEMENT PRIORITY FILTER
The audit is useful only if it changes what we do next.
DO NOW
• Provision environment • Configure real credentials • Run live smoke test • Run discovery engine • Contact New Cairo owners • Publish verified listings • Start host recruitment • Start first real bookings
WAIT
• Unclaimed listing + claim UX • Map-based search • Egyptian wallets • Reviews & ratings • Host analytics • Automated referral • Advanced cancellation UI
DO NOT DO NOW
• New discovery architecture • Mobile app • Real-time messaging • Enterprise scaling • Multi-AZ / CDN optimization • New audits just to plan more work • Any feature that does not help prove V1
StayOS • Management Situation • 14 Aug 2026

## Slide 13
RECOMMENDED MANAGEMENT DECISION
One clear decision
STOP BUILDING SUPPLY FEATURES. START USING THE SUPPLY ENGINE.
WHY
The discovery/import tooling is already sufficient for the Closed Alpha supply objective.
WHAT UNLOCKS VALUE
Real owner conversations → real verified listings → real bookings → evidence.
WHAT WE PROTECT
V1 scope discipline. No V2/V3 work before the marketplace proves itself.
NEXT SINGLE PRIORITY: Get the environment running, then activate the discovery → owner outreach → verified listing pipeline.
StayOS • Management Decision • Based on 14 Aug 2026 audit evidence

## Slide 14
SOURCE & GOVERNANCE NOTE
What this presentation is based on
PRODUCT_VERSION_ROADMAP_AUDIT.md — 2026-08-14: current product state, V1/V2/V3 boundaries, Discovery Engine and supply activation.
MANAGEMENT_SITUATION_ANALYSIS.md — 2026-08-14: current management diagnosis, blockers, critical path and decision.
07_FINAL_EXECUTIVE_DECISION.md — 2026-08-03: highest-authority MVP Gate and locked commercial conditions.
STAYOS_IMPLEMENTATION_BASELINE.md — 2026-07-27: engineering/alpha baseline.
P0_IMPLEMENTATION_REPORT.md — referenced by the audit for CSV template, import fix, owner outreach template and PENDING_VERIFICATION work.
Important: the audit itself states that historical chat was not used. Therefore, this deck distinguishes repository-backed facts from management interpretation.
CONFIDENCE
High for current repository state; historical 'what we agreed' is represented only where supported by the supplied audit/baseline evidence.
StayOS • Management Situation • 14 Aug 2026